## Example
Project Name | Processing Tutorials
Project Description | A set of instructional materials and assignments for the Processing "language" |  |  |  | September 18th
September 25th
Components | Milestone | Due Date | Goal % Complete | Actual % Complete | October 2nd
1. Installation and introduction to Processing | 1. Research installation | Friday, September 18th, 2020 | 100% | 100% | October 9th
| 2. Research Processing basics and description | Friday, September 18th, 2020 | 100% | 100%
| 3. Write instructional document: installation guide | Friday, September 18th, 2020 | 100% | 100% | October 16th
| 4. Write instructional document: Processing basics and description | Friday, September 25th, 2020 | 100% | 100%
| 5. Write assignment | Friday, September 25th, 2020 | 100% | 100%
| 6. Write hints to assignment | Friday, September 25th, 2020 | 100% | 100%
| 7. Write sample solution | Friday, September 25th, 2020 | 100% | 100% | October 23rd
2. Introduction to computer graphics concepts | 1. Research 2D graphics representations (shapes, coordinates, etc.) | Friday, October 2nd, 2020 | 100% | 100% | October 30th
| 2. Research 2D transformations | Friday, October 2nd, 2020 | 100% | 100%
| 3. Write instructional document: 2D representations | Friday, October 2nd, 2020 | 100% | 100%
| 4. Write instructional document: 2D transformations | Friday, October 2nd, 2020 | 100% | 100%
| 5. Write assignment | Friday, October 2nd, 2020 | 100% | 100% | November 6th
| 6. Write hints to assignment | Friday, October 2nd, 2020 | 100% | 100%
| 7. Write sample solution | Friday, October 2nd, 2020 | 100% | 100% | November 13th
3. Drawing basic shapes | 1. Research how to draw basic shapes in Processing | Friday, October 9th, 2020 | 100% | 100% | November 20th
| 2. Research color, stroke, and fill in Processing | Friday, October 9th, 2020 | 100% | 100%
| 3. Research 2D transformations in Processing | Friday, October 9th, 2020 | 100% | 100%
| 4. Write instructional document: basic shapes | Friday, October 9th, 2020 | 100% | 100%
| 5. Write instructional document: color | Friday, October 9th, 2020 | 100% | 100%
| 6. Write instructional document: transformations | Friday, October 9th, 2020 | 100% | 100%
| 7. Write assignment | Friday, October 9th, 2020 | 100% | 100% | December 4th
| 8. Write hints to assignment | Friday, October 9th, 2020 | 100% | 100%
| 9. Write sample solution | Friday, October 9th, 2020 | 100% | 100% | December 11th
4. Objects and Other Java Specifics in Processing | 1. Research classes | Friday, October 16th, 2020 | 100% | 100% | December 18th
| 2. Research functions | Friday, October 16th, 2020 | 100% | 100%
| 3. Research generics | Friday, October 16th, 2020 | 100% | 100%
| 4. Research using Java libraries | Friday, October 16th, 2020 | 100% | 100%
| 5. Research using Processing in pure Java | Friday, October 16th, 2020 | 100% | 100%
| 6. Write instructional document: classes | Friday, October 16th, 2020 | 100% | 100%
| 7. Write instructional document: functions | Friday, October 23rd, 2020 | 100% | 100%
| 8. Write instructional document: generics | Friday, October 23rd, 2020 | 100% | 100%
| 9. Write instructional document: Java libraries | Friday, October 23rd, 2020 | 100% | 100%
| 10. Write instructional document: pure Java | Friday, October 23rd, 2020 | 100% | 100%
| 11. Write assignment | Friday, October 23rd, 2020 | 100% | 100%
| 12. Write hints to assignment | Friday, October 23rd, 2020 | 100% | 100% | Two weeks: animation, 3d, specifics
| 13. Write sample solution | Friday, October 23rd, 2020 | 100% | 100%
5. Images | 1. Research how to load images | Friday, October 30th, 2020 | 100% | 100%
| 2. Research how to display images | Friday, October 30th, 2020 | 100% | 100%
| 3. Research how to write to an image/pdf | Friday, October 30th, 2020 | 100% | 100%
| 4. Write instructional document: loading images | Friday, October 30th, 2020 | 100% | 100%
| 5. Write instructional document: displaying images | Friday, October 30th, 2020 | 100% | 100%
| 6. Write instructional document: writing images | Friday, October 30th, 2020 | 100% | 100%
| 7. Write assignment | Friday, October 30th, 2020 | 100% | 100%
| 8. Write hints to assignment | Friday, October 30th, 2020 | 100% | 100%
| 9. Write sample solution | Friday, October 30th, 2020 | 100% | 100%
6. Interactivity | 1. Research mouse interaction | Friday, November 6th, 2020 | 100% | 100%
| 2. Research keyboard interaction | Friday, November 6th, 2020 | 100% | 100%
| 3. Write instructional document: mouse | Friday, November 6th, 2020 | 100% | 100%
| 4. Write instructional document: keyboard | Friday, November 6th, 2020 | 100% | 100%
| 5. Write assignment | Friday, November 6th, 2020 | 100% | 100%
| 6. Write hints to assignment | Friday, November 6th, 2020 | 100% | 100%
| 7. Write sample solution | Friday, November 6th, 2020 | 100% | 100%
7. Animation | 1. Research animation specifics in Processing | Friday, November 13th, 2020 | 100% | 100%
| 2. Write instructional document: animation | Friday, November 13th, 2020 | 100% | 100%
| 3. Write instructional document: specific reusable examples of animation | Friday, November 13th, 2020 | 100% | 100%
| 4. Write assignment | Friday, November 13th, 2020 | 100% | 100%
| 5. Write hints to assignment | Friday, November 13th, 2020 | 100% | 100%
| 6. Write sample solution | Friday, November 13th, 2020 | 100% | 100%
8. Math in Processing | 1. Research trigonometry in Processing | Friday, November 20th, 2020 | 100% | 100%
| 2. Research random values in Processing | Friday, November 20th, 2020 | 100% | 100%
| 3. Research miscellaneous math functions in Processing | Friday, November 20th, 2020 | 100% | 100%
| 4. Research vectors in Processing | Friday, November 20th, 2020 | 100% | 100%
| 5. Write instructional document: trig | Friday, November 20th, 2020 | 100% | 100%
| 6. Write instructional document: randomness | Friday, November 20th, 2020 | 100% | 100%
| 7. Write instructional document: miscellaneous | Friday, November 20th, 2020 | 100% | 100%
| 8. Write instructional document: vectors | Friday, November 20th, 2020 | 100% | 100%
| 9. Write assignment | Friday, November 20th, 2020 | 100% | 100%
| 10. Write hints to assignment | Friday, November 20th, 2020 | 100% | 100%
| 11. Write sample solution | Friday, November 20th, 2020 | 100% | 100%
9. Text | 1. Research how to display basic text | Friday, December 4th, 2020 | 100% | 100%
| 2. Research how to use fonts and text effects | Friday, December 4th, 2020 | 100% | 100%
| 3. Write instructional document: basic text | Friday, December 4th, 2020 | 100% | 100%
| 4. Write instructional document: fonts and effects | Friday, December 4th, 2020 | 100% | 100%
| 5. Write assignment | Friday, December 4th, 2020 | 100% | 100%
| 6. Write hints to assignment | Friday, December 4th, 2020 | 100% | 100%
| 7. Write sample solution | Friday, December 4th, 2020 | 100% | 100%
10. Introduction to 3D Sketches in Processing | 1. Research how to use a 3D renderer/mode | Friday, December 11th, 2020 | 100% | 100%
| 2. Research basic shapes in 3D | Friday, December 11th, 2020 | 100% | 100%
| 3. Research lights and camera in 3D | Friday, December 11th, 2020 | 100% | 100%
| 4. Research materials in 3D | Friday, December 11th, 2020 | 100% | 100%
| 5. Write instructional document: 3D mode | Friday, December 11th, 2020 | 100% | 100%
| 6. Write instructional document: basic shapes | Friday, December 11th, 2020 | 100% | 100%
| 7. Write instructional document: lights and camera | Friday, December 18th, 2020 | 100% | 20%
| 8. Write instructional document: materials | Friday, December 18th, 2020 | 100% | 100%
| 9. Write instructional document: anything else I learn during research | Friday, December 18th, 2020 | 100% | 100%
| 10. Write assignment | Friday, December 18th, 2020 | 100% | 100%
| 11. Write hints to assignment | Friday, December 18th, 2020 | 100% | 100%
| 12. Write sample solution | Friday, December 18th, 2020 | 100% | 100%
Notes: I am responsible for the entirety of the project. Due to the nature of this project, most milestones do not have testing requirements. However, for the milestones titled "Write sample solution", each test is as follows: - The test is a check of whether the sample solution produces the output as described in the corresponding assignment document. - I expect each sample solution to pass the above test. - If a "Write sample solution" is marked as 100% completed, you may assume that it has been tested and found to be correct. - Artifacts will be video/screenshot of sample solution running, with the corresponding assignment document.